## Sheet2
Proposed estimate for cutting bushes and cleaning garbage at village ....................... for prevention of Dangue under .................................... Gram Panchayat though M.G. N.R.E.G.S.-2018-19 within .......................P.S
Co-ordinate:- |  |  | ...............................................
Scheme Code-............................... | [5 empty] | Sansad ..................................
A
Cleaning of weeds, bushes and small hyacinth or surface dressing of the ground including removing vegetation and equalities from road side or village channel and others places
|  | Length in m. | breadth in m |  | area m2 |  |  | Mandays in Nos
road side | 2 | 1000 | 3 |  | 6000
road side | 2 | 500 | 2.5 |  | 2500
road side | 2 | 500 | 2.5 |  | 2500
road side | 2 | 500 | 2.5 |  | 2500
road side | 2 | 689 | 2.5 |  | 3445
road side | 2 | 585 | 2.5 |  | 2925
road side | 2 | 200 | 2.6 |  | 1040
road side | 2 | 150 | 3.5 |  | 1050
other place | 3 | 300 | 4 |  | 3600
other place | 2 | 450 | 3.5 |  | 3150
other place | 5 | 300 | 4 |  | 6000
other place | 2 | 450 | 3.5 |  | 3150
| Total |  |  |  | 37860
| Unskill mandays |  |  | 50 | m2/MD |  |  | 757
Unskill mandays for creach helper | [7 empty] | 8
Unskill mandays fordrinking watwr carrier | [7 empty] | 16
| Total unskill mandays | [6 empty] | 781
[6 empty] | Say |  | 781
|  | Total wage cost @ |  |  | 180 | /day = | Rs: | 140580
B.
1 | Semi Skilled for Supervision. 1ssk/50usk |  |  |  | 16 | 270 |  | 4320
2 | Cost for creche shed |  |  |  | L.S |  |  | 2000
3 | Cost for temp. toilet for women | [6 empty] | 1200
5 | Cost of board, first-aid and photo |  |  |  | L.S |  |  | 3500
|  |  | Total Non-wage cost |  |  |  |  | 11020
|  | Total project cost |  |  |  |  | Rs: | 151600
[6 empty] | say | Rs: | 151600
prepared by Skill Technical Person ..................... G.P |  |  |  | Vetted By Nirman Sahayak ..................... G.P
Prodhan ..................... G.P